## VAM CICD Checklist
CI TASKS
Task / Activity | Team Responsible | Status | Validation | Comments
Multibranch pipeline configuration | WUBS Accenture CI/CD Team | DONE | Completed
CloudBees Jenkins GitLab project integration | WUBS Accenture CI/CD Team | DONE | Completed
Jenkins agent integration with proper container | WUBS Accenture CI/CD Team | DONE | Completed
Compile and package maven artifacts in pipeline | WUBS Accenture CI/CD Team | DONE | Completed
SonarQube integration with CI pipeline | WUBS Accenture CI/CD Team | DONE | Completed
CheckMarx integration with CI pipeline | WUBS Accenture CI/CD Team | DONE | Completed
Jfrog Artifactory integration with CI pipeline to | WUBS Accenture CI/CD Team | DONE | Completed
Push the docker images in designated repository | WUBS Accenture CI/CD Team | DONE | Completed
XRAY scan of the pushed image in Jfrog Artifactory | WUBS Accenture CI/CD Team | DONE | Completed
Send notification mail after completion of the CI pipeline | WUBS Accenture CI/CD Team | DONE | Completed
Create Helm package for the project and commit it in the GitLab repo | WUBS Accenture CI/CD Team | DONE | Completed
Shared Library integration with CI pipeline | WUBS Accenture CI/CD Team | NYD |  | needs discussion with CCOE team
Helm artifacts in Jfrog Artifactory | WUBS Accenture CI/CD Team | NYD
Maven artifacts upload | WUBS Accenture CI/CD Team | NYD
Code versioning strategy | WUBS Accenture CI/CD Team | NYD |  | needs discussion with CCOE team
Environment/CD TASKS
Task / Activity | Team Responsible | Status | Validation | Comments
Spinnaker Application creation for a particular project | CCOE | DONE | Completed
Give read/write/execute permission to developers to create pipeline on that application | CCOE | DONE | Completed
Create EKS cluster in AWS | CCOE | DONE | Completed
Create Account of the EKS Cluster in Spinnaker for Deploy stage | CCOE | DONE | Completed
Create GitLab account in spinnaker to get Helm packages in bake stage | CCOE | DONE | Completed | One time set up for WUBS
Create controller to get CI Jenkins jobs in spinnaker | CCOE | DONE | Completed
Create secrets in K8s cluster to pull the docker images from jfrog artifactory | CCOE | DONE | Completed | Need to transfer the ownership from CCOE to WUBS
Create CD pipeline inside in Spinnaker Application | WUBS Accenture CI/CD Team | DONE | Completed
Create GITLAB REST API for the Helm tgz file | WUBS Accenture CI/CD Team | DONE | Completed
In the Bake stage under HELM3 put the GITLAB REST API for the Helm tgz file | WUBS Accenture CI/CD Team | DONE | Completed
Configure base64 encoded artifact as the output of the bake stage | WUBS Accenture CI/CD Team | DONE | Completed
Create deploy stage for the helm baked base64 encode artifact in the EKS cluster | WUBS Accenture CI/CD Team | DONE | Completed
Add validation stage to validate the succesful deployment in the EKS cluster | WUBS Accenture CI/CD Team | NYD |  | Need to look into it
Spinnaker pipeline auto trigger with Jenkins | WUBS Accenture CI/CD Team | DONE | Completed
CD Pipelines for higher environment | WUBS Accenture CI/CD Team | NYD |  | needs discussion with CCOE team and WUBS
Code promotion strategy for QA and higher environment | WUBS Accenture CI/CD Team | NYD |  | needs discussion with CCOE team and WUBS
Application validation |  | NYD |  | Load balancer service needs to be created and Route53 to be configured to expose the load balacer. Need to send email with all the details to TCS-CloudRelTeam@westernunion.com to provision Route53.

## Problem statements
FOR CI
Script approval in jenkins file for pipeline .
FOR CD
Unable to validate the k8s secrets in the cluster
Detailed Pod error log is not visible in case of any error
Configured Spinnaker users is not shwoing up in the spinnaker user group,only showing up in the admin group hence auto triggering is not happening